# 1-Week Sprint Task Assignment

Health & Fitness Monitoring System

ASP.NET Core 8.0 | MVP Release | 5 Developers

# 1. Team Assignment

| Dev | Role | Responsibility |
| --- | --- | --- |
| DEV-1 | Lead / Architect | Project setup, Database, Identity, Authentication |
| DEV-2 | Backend | Activity module (CRUD + calorie calculation) |
| DEV-3 | Backend | Nutrition module + Dashboard |
| DEV-4 | Backend | Goals module + Admin panel |
| DEV-5 | Frontend | All Razor Views + Layout + Styling |

# 2. Daily Schedule

## Day 1 (Monday) - Setup

| Dev | Tasks |
| --- | --- |
| DEV-1 | Create project, all Entity models, DbContext, run migration → Push by 2PM |
| DEV-2 | Create ActivityController (Index, Create), ActivityViewModel |
| DEV-3 | Create NutritionController (Index, Create), HomeController shell |
| DEV-4 | Create GoalController (Index, Create), Admin Area structure |
| DEV-5 | Create _Layout.cshtml with Bootstrap 5 navbar |

## Day 2 (Tuesday) - Core CRUD

| Dev | Tasks |
| --- | --- |
| DEV-1 | Complete AccountController (Login, Register, Logout), configure Identity |
| DEV-2 | Complete Activity CRUD (Edit, Delete, Details), add calorie calculation |
| DEV-3 | Complete Nutrition CRUD, implement daily totals calculation |
| DEV-4 | Complete Goal CRUD, create AdminController with user list |
| DEV-5 | Create Login, Register, Activity views (Index, Create, Edit) |

## Day 3 (Wednesday) - Features Complete

| Dev | Tasks |
| --- | --- |
| DEV-1 | Add Admin role, seed admin user, security review |
| DEV-2 | Test Activity module, fix bugs, add user filtering |
| DEV-3 | Complete Dashboard with summary cards, test Nutrition module |
| DEV-4 | Add user activate/deactivate in Admin, test Goals module |
| DEV-5 | Create Nutrition, Goal, Dashboard, Admin views |

## Day 4 (Thursday) - Testing

| Dev | Tasks |
| --- | --- |
| DEV-1 | Integration testing, test auth flows, prepare deployment config |
| DEV-2 | End-to-end testing of Activity workflow, bug fixes |
| DEV-3 | End-to-end testing of Nutrition + Dashboard, bug fixes |
| DEV-4 | End-to-end testing of Goals + Admin, bug fixes |
| DEV-5 | Responsive testing (mobile/tablet), UI fixes |

## Day 5 (Friday) - Delivery

| Dev | Tasks |
| --- | --- |
| ALL | Final bug fixes, create README, deploy, demo presentation |

# 3. Critical Rules

- DEV-1 must push project to Git by Day 1, 2:00 PM (blocks everyone)

- Daily standup at 9:00 AM (15 min)

- All code pushed by 5:00 PM daily

- Blocked > 30 min? Message team immediately

- Pull from main every morning before starting

# 4. MVP Scope

## Included

Register, Login, Logout | Activity CRUD | Nutrition CRUD | Goals CRUD | Dashboard (summary cards) | Admin (user list, lock/unlock)

## Excluded (Phase 2)

Password reset email | Charts | Notifications | Auto goal tracking | Filtering | System logs

# 5. Team Sign-Off

| Dev | Name | Signature | Date |
| --- | --- | --- | --- |
| DEV-1 |  |  |  |
| DEV-2 |  |  |  |
| DEV-3 |  |  |  |
| DEV-4 |  |  |  |
| DEV-5 |  |  |  |

— End of Document —